## Start here
Full event checklist
SAMPLE-FREE. No event-specific data: every row is a generic task, workstream and done-when, restructured from the six phase tables on the event management checklist page.
Phase
Phase 1: As soon as the event is approved | 9
Phase 2: Planning and booking | 10
Phase 3: Build | 10
Phase 4: The final two weeks | 10
Phase 5: Event day | 9
Phase 6: The week after, and the debrief | 8

## Phase 1
Phase 1: As soon as the event is approved
Done | Task | Workstream | Done when
[ ] | Write the outcome: what should be true 30 days after the event | Whole event | One sentence someone could check later, agreed by the executive sponsor
[ ] | Write the success criteria before anyone is assigned a task | Whole event | A short written list of what the event must deliver, agreed before the first task is handed out
[ ] | Name the executive sponsor | Whole event | The sponsor is named in the brief and has agreed to make the final call when two reasonable options collide
[ ] | Decide who the event is for | Whole event | The audience is written in one line: who should be in the room, and why they would come
[ ] | Set the budget range, with a contingency line | Whole event | A range someone with authority has agreed to, and a named approver for the contingency
[ ] | Pick the date window | Venue and logistics | A month or a season agreed, checked against the calendars of the people you most want in the room
[ ] | Start the event brief | Whole event | Purpose, audience, date window, budget range and owner fit on one page, and everyone planning works from the same version
[ ] | Decide which workstreams this event needs | Whole event | Workstreams that don't apply are deleted from the checklist, not left empty
[ ] | Name one owner for each workstream you kept | Whole event | Every workstream has exactly one name against it

## Phase 2
Phase 2: Planning and booking
Done | Task | Workstream | Done when
[ ] | Shortlist venues against the brief | Venue and logistics | Each option is checked for format, budget line, date and the technology you plan to use
[ ] | Book the venue | Venue and logistics | Contract signed, date confirmed in writing, and a named contact at the venue
[ ] | Book the other vendors the event needs, such as catering, AV and printing | Venue and logistics | Each vendor has confirmed a date, a deliverable and a contact
[ ] | Draft the agenda by segment | Content and program | Every segment has a purpose, a length and a line on what the guest leaves with
[ ] | Confirm speakers and the host | Content and program | Each speaker has agreed to a topic and a slot in writing
[ ] | Choose one theme | Brand and theme | The theme fits in one line and is written into the brief
[ ] | Build the guest list | Guest communications | Every name has a reason to be in the room and a relationship owner on your side
[ ] | Send the invitation | Guest communications | Sent, asking for dietary and access needs, with replies tracked in one place and one named person answering them
[ ] | Decide what proof the event should leave behind | Proof capture | Photos, testimonials and guest feedback each have a plan and an owner
[ ] | Arrange travel and hotel, if guests or your team are traveling | Venue and logistics | Rooms and travel are booked, or guests have been told exactly how to book

## Phase 3
Phase 3: Build
Done | Task | Workstream | Done when
[ ] | Write the opening story or keynote | Content and program | The script is finished and the executive sponsor has read it
[ ] | If guests will use the product, build the demo around a task they finish | Product or demo readiness | The demo ends with each guest holding something they made or set up, not just something they watched
[ ] | Lock the version of the product guests will use | Product or demo readiness | No changes after an agreed date, and that version has been tested end to end
[ ] | Set up guest access or hands-on materials | Product or demo readiness | Every confirmed guest has working access or a set of materials, tested before the day
[ ] | Name the fallback if the network or the product fails | Product or demo readiness | The fallback is written down, with the name of whoever makes the call to use it
[ ] | Carry the theme through every touchpoint | Brand and theme | Invitation, badges, agenda screen, food and drink, swag and thank-you have each been checked against the theme
[ ] | Order signage, printed materials and swag | Brand and theme | Ordered, with delivery dates that land before the freeze
[ ] | Write every guest email, each with its send date | Guest communications | Seat confirmation, one-week email, night-before email and thank-you are written in final form, dated, with a named sender
[ ] | Share the guest emails with everyone working the event | Guest communications | Everyone on the team has read what the guests will read
[ ] | Write the run of show | Day-of operations | Every segment has a start time, an owner and a cue

## Phase 4
Phase 4: The final two weeks
Done | Task | Workstream | Done when
[ ] | Switch to daily written check-ins | Whole event | Every Blocked or In Progress task gets a written update each day
[ ] | Reconfirm every vendor | Venue and logistics | Each vendor has confirmed time, place and on-the-day contact
[ ] | Send the final guest count, with dietary and access needs, to the venue and caterer | Venue and logistics | The count and the needs are sent by the venue's deadline and acknowledged
[ ] | Send the seat confirmation, the one-week email and the night-before email on their dates | Guest communications | Each goes out on its send date, and every reply has an owner
[ ] | Schedule the rehearsal and the team walkthrough | Day-of operations | Time, place and who attends are on the calendar for the day before the event
[ ] | Ship materials to the venue | Venue and logistics | Shipped, addressed to a named person, with tracking sent to whoever runs the day
[ ] | Write the handoff notes for whoever runs the day | Day-of operations | The notes cover what is in each box and where it goes, what to switch on and by when, what the venue is placing, which photos to take, and who is on call
[ ] | Put the debrief on the calendar | Whole event | The invitation has gone to the people who need to be there, before the event
[ ] | Pull the outstanding items list three days out | Whole event | Every open item is on one list with one name and a time beside it
[ ] | Freeze the plan two days out | Whole event | Every task is Ready for Review or Complete, and nothing is In Progress on rehearsal day

## Phase 5
Phase 5: Event day
Done | Task | Workstream | Done when
[ ] | Walk the room before doors open | Day-of operations | Every station is set against the handoff notes, and the tech is switched on by the agreed time
[ ] | Open check-in | Day-of operations | Check-in is staffed, with the guest list and materials in place, before the first guest arrives
[ ] | Run the event from the run of show | Day-of operations | Each segment starts with its owner in place, and any change goes through one named decision-maker
[ ] | Staff the tech table during hands-on segments | Product or demo readiness | One named person is at the tech table whenever guests are using the product
[ ] | Give the reminders in the handoff notes | Day-of operations | Each reminder is given at its time, to the person the notes name
[ ] | Take every photo on the photo list | Proof capture | Every shot on the list is taken and saved where the team can find it
[ ] | Capture testimonials and feedback in the room | Proof capture | Testimonial questions are asked of the guests who agreed, and feedback is collected before guests leave
[ ] | Keep someone on call | Whole event | The person on standby is reachable for the whole event window
[ ] | Send the thank-you email the same evening | Guest communications | Sent on the evening of the event, naming what guests actually did

## Phase 6
Phase 6: The week after, and the debrief
Done | Task | Workstream | Done when
[ ] | Write personally to the guests who gave the strongest feedback | Guest communications | Each has a personal note from their relationship owner within the week
[ ] | Give every follow-up an owner and a date | Whole event | No follow-up sits on the list without a name and a date beside it
[ ] | Send a feedback survey, if feedback wasn't collected in the room | Guest communications | Sent, with a closing date
[ ] | Gather the proof in one place | Proof capture | Photos, testimonials and feedback sit in one shared folder, with guest consent recorded
[ ] | Close out vendors against the budget | Venue and logistics | Every invoice is matched to its budget line, and any contingency spend is recorded with who approved it
[ ] | Hold the debrief against the outcome and the success criteria | Whole event | Each criterion is marked met, not met or too early to tell, with the evidence beside it
[ ] | Book the 30-day check | Whole event | A date 30 days after the event is on the calendar to answer the outcome sentence in writing
[ ] | Save the checklist for the next event | Whole event | The edited checklist, with this event's notes, is filed where the next event lead will find it