# Outstanding items checklist

[Event name]  |  Issued: [date]  |  Days to event: [3]

Everything on this page still needs a commitment, an owner, or a confirmation. If it has all three, it does not belong here. Issue it three days out. Reissue it daily until it is empty.

How to use it: one line per item. Say which of the three it is missing. Put one name on it. Put a time on it, not just a date.

| # | Item | Missing: commitment, owner or confirmation | One name | By when | Done |
| --- | --- | --- | --- | --- | --- |
| 1 | [ ] | [ ] | [ ] | [ ] | [ ] |
| 2 | [ ] | [ ] | [ ] | [ ] | [ ] |
| 3 | [ ] | [ ] | [ ] | [ ] | [ ] |

## Prompts: the things that are usually still open three days out

All Sample lines. Delete what does not apply.

### Guests

☐  Final registration push to anyone invited who has not answered

☐  Guest profiles finished, with how long each guest has worked with you

☐  Place cards and table assignments final

☐  Guest emails written and scheduled: one week, day before, thank-you

### Program

☐  One presentation deck, not one per speaker

☐  Printed agenda for each seat

☐  Small-group questions written for the table conversations

☐  Music and sound cues chosen and tested

### Room and look

☐  Signage for check-in, the tech table and the capture station

☐  Lighting

☐  Team look: what everyone is wearing

☐  Branded materials for the break activity

☐  Food and drink that carries the theme

☐  Welcome kit items counted against the guest list, plus spares

☐  Prizes bought and on site

### Proof and press

☐  Media and podcast invitation list, and the invitation script

☐  Media kit

☐  Plan for sound bites and b-roll: who, where, when

☐  Product flyer, printed and digital

### Communications

☐  Plan for communication during the event: who posts what, where

☐  Post-event communication plan

☐  Social push scheduled

### After

☐  Debrief on the calendar, with the people who need to be there

☐  Onboarding or implementation guide ready for guests who want to start

☐  Shipping and tracking details sent to the on-site lead