## Start here
The Event Ownership Matrix
EventsAuthority.com ¦ SAMPLE DATA: every task, date and role assignment in this file is a sample. Replace it with yours.
How to use it
1. On the Roles sheet, put a real name next to each role. The matrix uses roles, so it survives a change of people.
2. On the Matrix sheet, type your event date in cell C1. Every due date moves with it.
3. Filter the Preset column: Hosted, Trade show, or Both. Delete the rows you do not need. Add your own.
4. Give every row letters. R = does the work. A = owns the outcome. C = asked before. I = told after. R/A = both.
5. Read the Check column. Fix anything that is not OK.
The rules
One Accountable per row. Exactly one.
Every row has a doer: at least one R.
Blank is good. Keep C and I to the few people who truly need them.
Five statuses: Not Started, In Progress, Blocked, Ready for Review, Complete. Ready for Review means the doer is done and the Accountable has not signed yet.
Plan backward from event day. Every row has a due date. Link what depends on what.
Meet weekly for 15 minutes off the status board. In the last two weeks, check in daily in writing on anything Blocked or In Progress.
Freeze two days out: every row Ready for Review or Complete. Rehearsal day is for running it, not planning it.
RACI itself is a standard, public tool. What this file adds is the event layer: the phases, workstreams, gates and checks.
Built as a spreadsheet so it works anywhere. Read IMPORT-TEST.md before importing the CSV into a project tool.

## Roles
Code | Role | Name (yours) | Email (for import) | Owns
ES | Executive sponsor | Sample name |  | The story, the agenda call, who hosts, contingency calls
PL | Program lead | Sample name |  | Hands-on content, product go or no-go, feedback
EL | Event lead | Sample name |  | Venue, logistics, theme, swag, comms, check-in
PR | Product or technical lead | Sample name |  | Demo environment, accounts, live tech support
RL | Relationship lead | Sample name |  | Thank-you and follow-up with guests
BC | Booth captain | Sample name |  | The booth on the day and the team in it
SL | Sales lead | Sample name |  | Lead capture rules and follow-up ownership

## Matrix
SAMPLE | Event date: | 2027-06-15 | Change C1. All due dates follow.
ID | Phase | Workstream | Task | Preset | Status | Executive sponsor | Program lead | Event lead | Product or technical lead | Relationship lead | Booth captain | Sales lead | Due (days from event) | Due date | Depends on (ID) | A count | R count | C+I count | Check
S1 | 1 Before events season | Strategy and outcomes | Write what should be true 30 days after the event | Both | Not Started | A | C | R |  |  |  |  | -84
S2 | 1 Before events season | Strategy and outcomes | Agree success criteria (3 to 5, each one checkable) | Both | Not Started | A | C | R |  | C |  |  | -80 |  | S1
S3 | 1 Before events season | Strategy and outcomes | Name one Accountable owner per workstream | Both | Not Started | R/A |  | C |  |  |  |  | -77 |  | S2
S4 | 1 Before events season | Strategy and outcomes | Set the budget and who approves spend | Both | Not Started | R/A |  | C |  |  |  |  | -77 |  | S2
S5 | 1 Before events season | Strategy and outcomes | Build this matrix: rows, letters, due dates, dependencies | Both | Not Started | I |  | R/A |  |  |  |  | -70 |  | S3
C1 | 2 Before the show | Content and program | Narrative or keynote script | Hosted | Not Started | R/A | C |  | C |  |  |  | -21 |  | S2
C2 | 2 Before the show | Content and program | Demo flow and script (guests leave with real work done) | Hosted | Not Started |  | C |  | R/A |  |  |  | -14 |  | C1
C3 | 2 Before the show | Content and program | Hands-on segment design | Hosted | Not Started |  | A |  | R |  |  |  | -14 |  | C2
C4 | 2 Before the show | Content and program | Agenda sequencing and timing, with energy resets | Hosted | Not Started | A | C | R |  |  |  |  | -14 |  | C1
C5 | 2 Before the show | Content and program | Speaker prep and rehearsal (one row per speaker) | Hosted | Not Started | R/A |  | C |  |  |  |  | -2 |  | C2
V1 | 2 Before the show | Venue and logistics | Venue booking and host coordination | Both | Not Started | C |  | R/A |  |  |  |  | -56 |  | S4
V2 | 2 Before the show | Venue and logistics | AV order and tech check plan | Both | Not Started |  |  | R/A | C |  |  |  | -21 |  | V1
V3 | 2 Before the show | Venue and logistics | Catering and refreshments | Both | Not Started |  |  | R/A |  |  |  |  | -21 |  | V1
V4 | 2 Before the show | Venue and logistics | Room layout and seating plan | Hosted | Not Started | C |  | R/A |  | C |  |  | -7 |  | V1
V5 | 2 Before the show | Venue and logistics | Team travel and hotel | Both | Not Started |  |  | R/A |  |  |  |  | -35 |  | S4
B1 | 2 Before the show | Brand and theme | Theme system: one idea carried through every touchpoint | Both | Not Started | C |  | R/A |  |  |  |  | -49 |  | S2
B2 | 2 Before the show | Brand and theme | Signage and agenda-screen graphics | Both | Not Started |  |  | R/A |  |  |  |  | -21 |  | B1
B3 | 2 Before the show | Brand and theme | Swag and printed materials ordered, with ship-by date | Both | Not Started |  |  | R/A |  |  |  |  | -28 |  | B1
B4 | 2 Before the show | Brand and theme | Social content plan (before, during, after) | Both | Not Started | C |  | R/A |  |  |  |  | -14 |  | B1
B5 | 2 Before the show | Brand and theme | Photo and video shot list | Both | Not Started |  |  | R/A |  |  |  |  | -7 |  | B1
P1 | 2 Before the show | Proof capture | Media or video partner booked | Hosted | Not Started | I |  | R/A |  |  |  |  | -35 |  | S4
P2 | 2 Before the show | Proof capture | Testimonial candidates chosen | Hosted | Not Started | A |  | R |  | C |  |  | -7
P3 | 2 Before the show | Proof capture | Interview questions and talking points | Hosted | Not Started | A |  | R |  |  |  |  | -7 |  | P2
P4 | 2 Before the show | Proof capture | Capture station: location, sound, signage | Hosted | Not Started |  |  | R/A |  |  |  |  | -3 |  | P1
P5 | 4 The week after | Proof capture | Edit and distribute captured content | Hosted | Not Started | C |  | R/A |  |  |  |  | 14 |  | P4
D1 | 2 Before the show | Product and demo readiness | Feature freeze and QA | Hosted | Not Started |  | A |  | R |  |  |  | -10
D2 | 2 Before the show | Product and demo readiness | Guest accounts provisioned and activation sent | Hosted | Not Started |  |  |  | R/A | C |  |  | -7 |  | D1
D3 | 2 Before the show | Product and demo readiness | Demo environment set up and tested on a venue-like network | Hosted | Not Started |  |  |  | R/A |  |  |  | -5 |  | D1
D4 | 2 Before the show | Product and demo readiness | Fallback plan: what we do if the network or product fails | Both | Not Started | C | A |  | R |  |  |  | -5 |  | D3
D5 | 2 Before the show | Product and demo readiness | Quick-start guide for guests | Hosted | Not Started |  | C |  | R/A |  |  |  | -7 |  | C2
G1 | 2 Before the show | Guest communications | Invitation and RSVP tracking | Hosted | Not Started |  |  | R/A |  | C |  |  | -28 |  | B1
G2 | 2 Before the show | Guest communications | Email sequence written with send dates (invite, one week, day before, thank-you) | Both | Not Started | C |  | R/A |  |  |  |  | -21 |  | B1
G3 | 2 Before the show | Guest communications | Team briefed on everything guests will receive | Both | Not Started |  |  | R/A |  |  | I | I | -7 |  | G2
G4 | 4 The week after | Guest communications | Thank-you sent the same day | Both | Not Started |  |  | R |  | A |  |  | 0 |  | G2
G5 | 4 The week after | Guest communications | Feedback survey sent and results collected | Both | Not Started |  | A | R |  |  |  |  | 3
O1 | 2 Before the show | Day-of operations | Run of show document | Both | Not Started | A | C | R |  |  |  |  | -7 |  | C4
O2 | 2 Before the show | Day-of operations | MC or host named and briefed | Hosted | Not Started | R/A | [6 empty] | -7 |  | O1
O3 | 2 Before the show | Day-of operations | Outstanding items list issued (3 days out) | Both | Not Started | I |  | R/A |  |  |  |  | -3 |  | O1
O4 | 2 Before the show | Day-of operations | Handoff pack delivered to the on-site lead | Both | Not Started |  |  | R/A |  |  |  |  | -3 |  | O3
O5 | 3 At the show | Day-of operations | Rehearsal and room walkthrough (nothing In Progress today) | Both | Not Started | A |  | R | R |  |  |  | -1 |  | O4
O6 | 3 At the show | Day-of operations | Registration and check-in | Both | Not Started |  |  | R/A |  | C |  |  | 0 |  | O5
O7 | 3 At the show | Day-of operations | Live tech support | Both | Not Started |  |  |  | R/A |  |  |  | 0 |  | D3
O8 | 3 At the show | Day-of operations | Contingency calls on the day | Both | Not Started | A |  | R |  |  |  |  | 0 |  | D4
X1 | 1 Before events season | Sponsorship and show selection | Four evaluation questions answered for each candidate show | Trade show | Not Started | A |  | R |  |  |  | C | -120
X2 | 1 Before events season | Sponsorship and show selection | Prospectus and agenda reviewed; airtime confirmed in writing | Trade show | Not Started | C |  | R/A |  |  |  |  | -100 |  | X1
X3 | 1 Before events season | Sponsorship and show selection | Past-show baseline: cost per lead, traffic, customers | Trade show | Not Started |  |  | R/A |  |  |  | C | -100
X4 | 1 Before events season | Sponsorship and show selection | Sponsorship agreement signed | Trade show | Not Started | R/A |  | C |  |  |  |  | -84 |  | X2
X5 | 2 Before the show | Sponsorship and show selection | Organizer deliverables and deadlines tracked | Trade show | Not Started |  |  | R/A |  |  |  |  | -60 |  | X4
T1 | 2 Before the show | Booth and activation | Booth theme tied to brand story and the show's narrative | Trade show | Not Started | C |  | R/A |  |  |  |  | -70 |  | X4
T2 | 2 Before the show | Booth and activation | Booth build, graphics and shipping | Trade show | Not Started |  |  | R/A |  |  |  |  | -28 |  | T1
T3 | 2 Before the show | Booth and activation | Traffic driver: the reason to stop | Trade show | Not Started |  |  | R/A |  |  |  | C | -42 |  | T1
T4 | 2 Before the show | Booth and activation | Team briefing: message, look, talking points, booth rules | Trade show | Not Started |  |  | C |  |  | R/A | C | -3 |  | G2
T5 | 3 At the show | Booth and activation | Booth open, staffed and on schedule | Trade show | Not Started | [5 empty] | R/A |  | 0 |  | T4
L1 | 2 Before the show | Lead capture and follow-up | Capture method and fields agreed with sales | Trade show | Not Started |  |  | R |  |  |  | A | -28 |  | S2
L2 | 2 Before the show | Lead capture and follow-up | Three pre-show touches sent | Trade show | Not Started |  |  | R/A |  |  |  | C | -7 |  | G2
L3 | 3 At the show | Lead capture and follow-up | Daily booth sync: who owns which conversation | Trade show | Not Started | [5 empty] | R/A | C | 0 |  | L1
L4 | 4 The week after | Lead capture and follow-up | Follow-up sent, one owner per relationship | Trade show | Not Started |  |  | I |  |  |  | R/A | 3 |  | L3
L5 | 5 Back at the office | Lead capture and follow-up | Leads and pipeline counted at 30 days | Trade show | Not Started | I | [5 empty] | R/A | 30 |  | L4
Z1 | 4 The week after | Strategy and outcomes | Debrief held (booked before the event) | Both | Not Started | A | C | R |  |  |  |  | 5
Z2 | 5 Back at the office | Strategy and outcomes | 30-day outcome checked against the success criteria | Both | Not Started | A |  | R |  |  |  |  | 30 |  | Z1
Z3 | 5 Back at the office | Strategy and outcomes | Matrix saved as the template for the next event | Both | Not Started |  |  | R/A |  |  |  |  | 30 |  | Z1

## Dashboard
SAMPLE. Counts update from the Matrix sheet.
Role | Accountable on | Responsible on | Share of all A | Load
Executive sponsor
Program lead
Event lead
Product or technical lead
Relationship lead
Booth captain
Sales lead
Status | Rows
Not Started
In Progress
Blocked
Ready for Review
Complete
Rows needing a fix
Days to event