## Run of show
Run of show
SAMPLE: a half-day hosted launch. Replace every row. Change a Minutes cell and every later time moves.
Event: | [Event name] | Date: | [Date] | Room: | [Room]
On-site lead: | [Name, mobile] | On call: | [Name, mobile]
Doors / first start time: | 8:30
Start | End | Minutes | Segment | Owner (role) | What happens | What the guest leaves with | AV, screen and sound cue | If it goes wrong | Status
|  | 30 | Arrivals and check-in | Event lead | Badges, welcome kit, seat guests at assigned tables | A name badge and a reason to talk to the table | Walk-in music, agenda on screen | Second check-in person on standby if a queue forms | Not Started
|  | 30 | Breakfast and networking | Relationship lead | Hosts circulate; every guest is greeted by name | One new contact | Music down at minute 25, chime at minute 28 | If food is late, open with coffee and move the welcome up | Not Started
|  | 45 | Opening story | Executive sponsor | Why the old way is broken and what changes today | Sees their own business in the story | Slides, handheld mic | No slides: tell it from the podium; the story does not need them | Not Started
|  | 30 | Getting everyone set up | Product or technical lead | Guests log in on their own laptops; helpers at each table | A working login | Wi-Fi details on screen and on badge backs | Wi-Fi fails: switch to one presenter screen-share walkthrough | Not Started
|  | 30 | Demo with an outcome | Program lead | One real task done live, guests follow along | A piece of their own work finished | Screen-share, lapel mic | Pre-recorded run of the same task is loaded and ready | Not Started
|  | 5 | Energy reset | Program lead | Table-share: one question, two minutes per table | A laugh and a second wind | Question on screen | Skip if running more than 10 minutes late | Not Started
|  | 15 | Break with an activity | Event lead | Short themed contest with a prize; photos | A story to tell on the show floor | Music up | Shorten to 10 minutes if behind | Not Started
|  | 30 | Hands-on workshop | Program lead | Guests use the product on their own material | Proof of work done they can show a colleague | Helpers roam; timer on screen | Pair guests up if accounts fail | Not Started
|  | 30 | Feedback roundtable and close | Executive sponsor | What worked, what could be smoother; next step; thanks | Knows the next step and who to call | Two handheld mics | Collect written cards if the room is quiet | Not Started
|  | 30 | Testimonial capture and reset | Event lead | Chosen guests to the capture station; room struck | n/a | Capture station live | Book a call within the week instead | Not Started
Total minutes

## Day before
Day before and morning of
SAMPLE. Rehearsal day is for running it, not planning it. Nothing should still be In Progress.
When | What | Owner (role) | Done
Day before, 60 min | Team walkthrough in the room: presentation run, break plan, capture station, check-in, tech station | Executive sponsor
Day before | Boxes opened and counted against the handoff pack list | Event lead
Day before | Wi-Fi tested on three laptops; fallback screen-share tested | Product or technical lead
Day before, evening | Day-before email sent to guests | Event lead
Morning, 30 min before doors | Final room check: signage, lights on, table numbers, badges in order, music | Event lead
Morning | Speakers miked and slides loaded | Product or technical lead